## Causes
Categories | Codes | Merge with n. ? | Observation | Categories used
Input | Changing business needs |  |  | Input
People | Communication flaws between team and customer |  |  | Method
Input | Complexity of domain |  |  | Organization
Input | Complexity of project |  |  | People
Method | Complexity of RE |  |  | Tools
People | Conflict of interests at customer side
People | Conflict of interests at management level
People | Conflicting stakeholder viewpoints
Method | Customer does not formally approve the requirements
People | Customer does not know what he wants
People | Demotivation
Method | Documentation overhead
People | Gold plating
Input | High complexity in overall project setting
People | High quality expectation of customer
Organization | High workload
People | Inability to specify measurable non-functional requirements
Method | Inappropriate definition of contract
Method | Incomplete requirements
Method | Insufficient agility
Method | Insufficient analysis at the beginnging of the project
Method | Insufficient collaboration in process
Input | Insufficient information
Method | Insufficient planning of RE
Method | Insufficient resource plan
Organization | Insufficient resources
Method | Insufficient stakeholder analysis
Organization | Insufficient team size
Method | Lack of a well-defined RE process
Method | Lack of change management at customer side
People | Lack of creativity
People | Lack of discipline
People | Lack of experience of RE team members
People | Lack of interest about customers domain
Method | Lack of requirements management
People | Lack of teamwork skills
Method | Lack of time
People | Lack of trust
Other | Language barriers
Organization | Many customers
Input | Missing access to business needs
Method | Missing company wide standard
Method | Missing completeness check of requirements | 107
People | Missing concentration on business needs
Method | Missing customer involvement
Method | Missing direct communication to customer
People | Missing domain knowledge
People | Missing engagement by customer
Method | Missing involvement of developers
People | Missing IT project experience at customer side
People | Missing knowledge about development framework
Method | Missing knowledge transfer
People | Missing of a global view of the system
People | Missing prioritization by customer
People | Missing RE awareness at customer side
People | Missing RE awareness at team side
Tools | Missing requirements specification template
Method | Missing solution approach
Tools | Missing tool support
People | Missing willingless to change
Method | Non functional requirements unclear
People | Not following the communication plan
Organization | Oversized portfolio planning
Organization | Policy restrictions
Method | Poor project management
Method | Poor requirements elicitation techniques
Organization | Pressure to not exceed priminarily defined resources
Method | Process doesn't allow for innovation
People | Requirements engineer has no influence on customer
Method | Requirements remain too abstract
Method | Solution orientation
Input | Stakeholder fluctuation
People | Stakeholders lack business vision and understanding
Method | Strict time schedule by customer
People | Subjective interpretations
Organization | Team fluctuation
People | Thinking in legacy systems
Method | Too high team distribution
Organization | Unavailability of requirements engineer
Input | Unclear business needs
Input | Unclear project scope
Input | Unclear roles and responsibilities at customer side
Method | Unclear terminology
Input | Unexpected changes in requirements | 89
Input | Unfeasible goals
Input | Unfeasible requirements
Input | Volatile industry segment that leads to changes
Input | Volatile requirements
Input | Weak management at customer side
People | Weak qualification of RE team members
People | Weak qualification of stakeholders
Input | Workload of customer | 111
Add New Codes Here (marked in yellow)
People | Missing technical knowledge
People | Conflicts of personalities
People | Lack of leadership
Method | Lack of communication channels
Method | Lack of project management
People | Bad atmosphere in the group
People | Lack of training
Method | Missing documentation
Method | Rework |  | ? (weird to have rework as a cause)
Method | Concurrent development activities
People | Miscommunication between RE team
People | SE Team refrains from asking questions
Method | Missing check of requirements
Organization | High cost |  | ? (weird to have high cost as a cause)
Method | Missing methodology
Method | too many meetings
Input | Unavailability of stakeholder
Method | Missing communication to customer side
People | Different skill levels

## Effects
Categories | Codes | Merge with n. ? | Observation | Categories used
Project or Organization | Budget overrun |  |  | Customer
Project or Organization | Conflicts within the team |  |  | Design or Implementation
Customer | Customer dissatisfaction |  |  | Product
Product | Decreased business value |  |  | Project or Organization
Project or Organization | Decreased efficiency (overall) |  |  | Verification or Validation
Project or Organization | Decreased manageability
Verification or Validation | Decreased test efficiency
Customer | Decreased user acceptance
Verification or Validation | Delayed detection of bugs and failures
Verification or Validation | Delayed detection of missing functions
Project or Organization | Difficulties in project management
Project or Organization | Effort overrun | 54
Product | Implementation of irrelevant requirements
Product | Incomplete Requirements
Project or Organization | Increased communication
Project or Organization | Increased complexity in RE
Project or Organization | Increased difficulty of impact analyses
Project or Organization | Increased difficulty of requirements elicitation
Project or Organization | Increased maintenance costs
Project or Organization | Increased number of change requests
Product | Increased number of failures / bugs
Project or Organization | Increased number of requirements changes
Project or Organization | Inefficient development
Project or Organization | Information gets lost
Product | Lack of innovation
Project or Organization | Late decision
Project or Organization | Less time left for RE
Product | Missing functionality of product
Product | Missing traceability
Project or Organization | Misunderstanding (overall)
Design or Implementation | Need for post implementation
Design or Implementation | Need for support by a more experienced developer
Project or Organization | Overall demotivation
Design or Implementation | Poor (system) design quality
Product | Poor documentation of requirements
Product | Poor product quality
Product | Poor requirements quality (general)
Project or Organization | Project scope becomes unclear
Product | Solution becomes difficult to maintain
Product | Solution becomes more complex
Project or Organization | Solution orientation
Verification or Validation | Tests are of low quality
Project or Organization | Time overrun
Product | Unexpected non-functional requirements
Verification or Validation | Untestable requirements
Verification or Validation | Validation of requirements becomes difficult
Project or Organization | Weak knowledge transfer
Project or Organization | Wrong estimates
Product | Wrong sizing of hardware
Add New Codes Here (marked in yellow)
Project or Organization | Poor communication
Customer | Conflicts with the customer
Project or Organization | Rework